Planning Meeting for the Whangarei Quit Stall in the Mall

Monday 17th June 2013 at Manaia PHO

Present:	Ngaire Rae, Annie Mullenger, Erina K - Manaia PHO

Kapua Nathan - Ngati Hine Health Trust

Elizabeth Schultz, Maraea Mentor, Jan Marshall - NDHB

Purpose: to Finalise the arrangements for the Quit Stall in the Mall Pilot Project

A brief summary of discussions

1. Discussed the set up and learning’s from the recent World Smokefree Day Stall on Friday 31st May run by Ngati Hine Health Trust and Manaia PHO

Key points

Overall worked well, 15 people enrolled with Ngati Hine, gave advice to 49 people, Balloons a great draw card  for families, good to have men staffing the stall as well, lots of young people and people with babies spoken to, good to have pre-made packs available to save time on the day and something easy to hand over.

Demand was high and as soon as began setting up people arrived, was good to have a good number of people helping so people could be spoken to and have time spent with them. Worthwhile!

Kapua and Te Aniwa have sussed the business of the Mall on a Thursday which was slow on the day they went but looked to pick up later. Group acknowledges that there will be ebbs and flows throughout the pilot period – which will also be dependent on the weather.

2. Organisational commitment

As Annie’s contract is not being renewed and the PHO are looking to establish a different configuration there will be no similar role that can help with the stalls however Erina has a small amount of capacity and Ngaire is committed to participating.

Both NDHB and Ngati Hine reasserted their commitment.

3. Start Date, Timetable and other Agreements

It was agreed to hold the stalls on one specific day  per fortnight - a Thursday - starting 11th July then the 25th July, August 28th and 22nd, September 12th and 26th – Jan to send out an Outlook calendar request.

The details of resources, personnel, media and responsibilities were discussed and the Outcome is summarised in the attached Work Plan.

Key points

Stall set up 10.30 start – with briefing

All to wear green “Ask me about quitting T-shirts”

Minimum of one person - per organisation Maximum of 2 equals a total of 3 or 6 or the more the merrier especially if a Tane.

Will be counting a range of factors including Brief Advice, Referred, Enrolled and Info only.

People who are committed to quit to be referred to Ngati Hine or NHHT can enrol on the spot

Will try and record GP details, NDHB will refer to Quit Group if that is requested/chosen

AND..BIG UPS to Annie for her passionate commitment to this work – you will be missed!!

Quit Stall in the Mall Pilot - Work Plan

| Mission | Tasks/Resource provision | Responsibility | Compltd/Comment |
| --- | --- | --- | --- |
| Stall set up/ Resources | Gazebo Evaluation forms Banner – arrange design and creation of banner for stall | Ngarie to book “ to develop | Gazebo booked - NR Have requested artwork from HPA for banner - NR |
|  | “Flanners” Table Chairs? Resources tool kit – tape/ string/ pens etc etc Quit Cards Clip Boards Balloons Prizes – Quick Mist | NHDB – Liz and team - from PHU and own resources |  |
|  | Sample/starter quit Packs TV Monitor video for Ads Enrolment forms NRT “loose” Lozenge Jar? NHHT posters etc. | NHHT - Kapua |  |
| Mall site booking | Contact Council: to book site Try for site outside Orr’s Pharmacy with power for videos and Car/van access | Kapua |  |
| CO monitors | Smokelysers | All to bring if possible |  |
| Media and Advertising | Ngati Hine Community Notices and plug by morning DJ on the day if possible Community papers and other advertising Ngaire Kapua and Ngaire to discuss consistent key message and | Kapua Ngaire |  |
| Rewards for quitters | To explore idea of “rewards” for people who have recently quit as many attend the stall. | Liz to Scope with Warren from PHU |  |
| Prize for draw | Quit Mist to be donated Other prizes? How will draw work – need to suss How many Lozenges Jar? | NDHB – Jan and team Jan to discuss with Kapua |  |
| Team Briefing | Tune in and set goal/ targets | Kapua for the first time?? |  |
| Evaluation | Process and outcome evaluations to be undertaken “Tally” forms to be refined to collect all data – just adding column for consent to refer. Public need to know what info will be used for. Feedback sheet for the stand – each team to review what worked/what didn’t Manaia will follow up with GP referrals Impact Evaluation For people who have committed to quitting - follow up at 4 weeks and 3 months as per tier one specs. Ngati Hine – to follow –up own referrals Manaia the GP referrals NHDB the Quitline referrals If staff write a quit card will follow-up If want Champix get consent to contact the GP Champix – Ngati Hine have slips for people to take to Doctor. Questions at follow-up Did they make a quit attempt? If yes do 4 week and 3 month follow up If no – record what you can | Ngaire to lead and to collate the data form the stalls Ngaire to suss if Brief Advice at the Mall can be counted for primary Care Target Kapua to provide details of quit questions at 4 weeks and 3 months to Ngaire |  |

Availability for stall

Names of those who can’t make it on a specific date

| 11th July | 25th July | 8th August | 22nd August | 12th Sept | 26th Sept |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Jan |